## Slide 1: CMPG213 PROJECT SCOPE
Presented by Group 6:
50344226 – Kutloano Sabalele
50763679 – Lindokuhle Kweta
45662878 – Ruan Venter
55810608 – Reinhardt van der Walt
55807593 – Sibane Ndhlela
55985866 – Whandré Singleton
50536192 – Zizipho Zingelwa
Travel Agency Information System
Date presented: 2026/03/xx

## Slide 2: TABLE OF CONTENT
1. Background
2. Problem Statement
3. Constraints
4. Scope Definition
5. Goals for the Project
6. Opportunities to Improve
7. Schedule
8. Budget
9. Internal Resources

## Slide 3: 1. BACKGROUND
Ubuntu Travel (Travelling Better Together) is a franchised travel agency operating across South Africa. The company offers comprehensive travel solutions to private (local and international) and corporate clients:
Booking accommodation with their nation-wide, inhouse accommodation.
Managing transport – coordination of flights, car rentals, and bus shuttles.
Managing clients’ trip expenses and itineraries tailored to their preferred leisure activities.
Their brand embodies a trusted travel companion, comfort and relaxation.

## Slide 4: 2. PROBLEM STATEMENT
The agency expanded rapidly after extending its services to international clients. Travel agents are overwhelmed with telephonic inquiries, bookings, and customer service demands, leading to inefficiencies and delays.
Management lacks timely facts for decision-making due to slow, manual reporting and heavy employee workloads.
Administrative processes are disorganized with notes in personal notebooks as the leading contributing factor.
Customers are dissatisfied with slow response times, harming the agency’s reputation.

## Slide 5: 3. CONTRAINTS
Project budget: R2,000,000.00
The System Analysts, Designers, and Builders are all students with limited prior enterprise-level system design.
The project must be fully developed, tested, and implemented by 30 September 2026.

## Slide 6: 4. SCOPE DEFINITION
The system must have the following functionality:
Maintaining system users and access
Maintaining attractions
Maintaining accommodation
Maintaining transport
Managing trip expenses
Managing itineraries
Exporting data to Excel and PDF
Reporting on operational activities through graphical visual elements

## Slide 7: 5. PROJECT GOALS
5.1. IMPROVING PROCESSES:
Reduce time spent on compiling reports by automating reporting.
Track progress on client inquiries by logging trips on the system instead of making notes in notebooks.
5.2. IMPROVING KNOWLEDGE:
Create reports to identify seasonal trends, tourism hotspots, and frequently used car rentals.
Create reports to analyze revenue generated, profit, loss and average money spent per client.
Create reports to highlight employee performance and operational inefficiencies to improve

## Slide 8
5.3. IMPROVING COMMUNICATION:
Improve agent response times to customers by creating reports to highlight employee performance and operational inefficiencies, providing management with a platform to give agents targets.
Take pressure off agents by creating a client portal to view, select and submit all accommodation and transport options, and leisure activities, with costs included, which will notify the agent on the system.
Provide international clients with a currency conversion calculator.

## Slide 9: 6. OPPORTUNITIES TO IMPROVE
Develop a module to indicate the stock location of car rentals to identify where there are surpluses or shortages of rentals.
  Reason: Some cars are used more often than others due to convenience of their location.
  Benefit: Ensures cars don’t overrun their kilometer warranties prematurely by distributing vehicles proportionally.
Develop a module to manage car rental maintenance schedules
  Reason: Service records are not fully complaint to safety compliance standards.
  Benefit: Safety audit records are accessible on the system.
Develop functionality for all trip itineraries to be exported to PDF documents.
  Reason: Some rural regions have limited to no internet connection.
  Benefit: Client can download and save their itineraries offline which are accessible at anytime.

## Slide 10: 7. PROJECT SCHEDULE
Phase | Description | Proposed Date
Scope definition | Scope definition documented in the project proposal. | 2026/03/02
Problem analysis | Define existing problems, propose solutions, identify business opportunities, and establishing constraints. | 2026/03/02
Requirement analysis | Business requirement statements | 2025/03/23
Logical design | Specifications and the logical system modules | 2026/04/14
Decision analysis | Candidate solution evaluation and selection in terms of technical, operational, economic, schedule, and risk feasibility. | 2026/05/04
Physical design & integration | Design models, detail specifications, develop prototypes, and redesign business processes. | 2026/07/24
Construction & testing | Develop the database, custom-built software, and user interfaces (Windows or Web). Create a thorough test plan. | 2026/08/14
Installation | Conclude the project with delivery of a fully operational product, review document quality, and provide an operational manual. | 2026/09/30

## Slide 11: 8. BUDGET
Expense | Description | Calculation | Amount
Hardware | New computer used as a server to store database information. |  | R 50,000.00
Software | Visual Studio Professional license | R1,600.00 per month * 8 months | R12,800.00
Software | Microsoft 365 Business Standard | R200.00 per month * 8 months | R1,600.00
Salaries | Labor employed for the project’s development. | 192 per hour x 180 hours per month x 7 employees x 8 months | R1,935,360.00
Total budget |  |  | R1,999,760.00

## Slide 12: 9. INTERNAL RESOURCES
The suggested internal resources for the project are:
System Owner (Sponsor): Mr Vincent Govender.
The following system users are proposed and should be available for 15% of their time for 8 months:
Travel agents Precious Moeketsi and Liam Du Preez